## Gantt chart template
Gantt chart template
Task Name | Start Date | End Date | Duration (Days) | Team Member | Percentage completed | Days complete | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR
Project 1
Task 1 | 2023-12-04 | 2023-12-08 | 5 | Mark | 95% | 4.75 | bar: WEEK 1 MO to WEEK 1 FR
Task 2 | 2023-12-11 | 2023-12-13 | 3 | Helen | 89% | 2.67 | bar: WEEK 2 MO to WEEK 2 WE
Task 3 | 2023-12-13 | 2023-12-15 | 3 | Jen | 56% | 1.68 | bar: WEEK 2 WE to WEEK 2 FR
Task 4 | 2023-12-18 | 2023-12-19 | 2 | Carlos | 45% | 0.9 | bar: WEEK 3 MO to WEEK 3 TU
Task 5 | 2023-12-19 | 2023-12-22 | 4 | Annie | 23% | 0.92 | bar: WEEK 3 TU to WEEK 3 FR
Project 2
Task 1 | 2023-12-25 | 2023-12-27 | 3 | David | 100% | 3 | bar: WEEK 4 MO to WEEK 4 WE
Task 2 | 2023-12-27 | 2023-12-29 | 3 | Kyle | 95% | 2.85 | bar: WEEK 4 WE to WEEK 4 FR
Task 3 | 2024-01-08 | 2024-01-09 | 2 | Annie | 34% | 0.68 | bar: WEEK 5 MO to WEEK 5 TU
Task 4 | 2024-01-10 | 2024-01-12 | 3 | Jen | 22% | 0.66 | bar: WEEK 5 WE to WEEK 5 FR
Task 5 | 2024-01-15 | 2024-01-15 | 1 | Millie | 2% | 0.02 | bar: WEEK 6 MO
Project 3
Task 1 | 2024-01-17 | 2024-01-19 | 3 | Helen | 87% | 2.61 | bar: WEEK 6 WE to WEEK 6 FR
Task 2 | 2024-01-22 | 2024-01-26 | 5 | Jen | 58% | 2.9 | bar: WEEK 7 MO to WEEK 7 FR
Task 3 | 2024-01-29 | 2024-01-31 | 3 | Henry | 72% | 2.16 | bar: WEEK 8 MO to WEEK 8 WE
Task 4 | 2024-02-01 | 2024-02-02 | 2 | Carlos | 52% | 1.04 | bar: WEEK 8 TH to WEEK 8 FR
Task 5 | 2024-02-05 | 2024-02-09 | 5 | David | 10% | 0.5 | bar: WEEK 9 MO to WEEK 9 FR
Formulas:
Duration (Days) = NETWORKDAYS([Start Date],[End Date])